## Critical Path Schedule
Task Number | Predecessor | Optimistic | Most Likely | Pessimistic | Average | Standard Deviation | Risk Event Probability | Risk Event
Task 1 | - | 6 | 9 | 12 | 9 | 1.2247 | 10% | R1
Task 2 | - | 2 | 4 | 6 | 4 | 0.8165 | 25% | R4
Task 3 | Task 1 and 2 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R2, R3
Task 4 | Task 3 | 4 | 8 | 9 | 7 | 1.0801
Total Duration |  |  |  |  | 21
Wrong Duration

## Risk Event Matrix
Task Number | Optimistic | Most Likely | Pessimistic | Average | Standard Deviation | Risk Event Probability | Risk Event | Risk Event Impact (Days)
Task 1 | 6 | 9 | 12 | 9 | 1.2247 | 10% | R1 | 2
Task 2 | 2 | 4 | 6 | 4 | 0.8165 | 25% | R4 | 9
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R2 | 16
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R3 | 20
Task 4 | 4 | 8 | 9 | 7 | 1.0801
Duration |  |  |  | 21

## Simulation
Task Number | Optimistic | Most Likely | Pessimistic | Average | Standard Deviation | Risk Event Probability | Risk Event | Risk Event Impact (Days) |  | Task 1 Value | Risk 1 Value | Total Task 1 | Task 2 Value | Risk 2 Value | Total Task 2 | Task 3 Value | Risk 3 Value | Risk 4 Value | Total Task 3 | Task 4 Value | Critical Path Total T1,T3,T4
Task 1 | 6 | 9 | 12 | 9 | 1.2247 | 10% | R1 | 2 |  | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 7 | 34
Task 2 | 2 | 4 | 6 | 4 | 0.8165 | 25% | R4 | 9 |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 34
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R2 | 16 |  | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 55
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R3 | 20 |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 55
Task 4 | 4 | 8 | 9 | 7 | 1.0801 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 5 | 33
[5 empty] | Duration |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[5 empty] | 1 |  |  |  |  | 8 | 0 | 8 | 2 | 9 | 11 | 6 | 0 | 0 | 6 | 6 | 20
[5 empty] | 2 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 17
[5 empty] | 3 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 56
[5 empty] | 4 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 5 | 15
[5 empty] | 5 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 22
[5 empty] | 6 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 4 | 38
[5 empty] | 7 |  |  |  |  | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 37
[5 empty] | 8 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 7 | 37
[5 empty] | 9 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 39
[5 empty] | 10 |  |  |  |  | 8 | 0 | 8 | 1 | 9 | 10 | 6 | 0 | 20 | 26 | 7 | 41
[5 empty] | 11 |  |  |  |  | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 42
[5 empty] | 12 |  |  |  |  | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 8 | 22
[5 empty] | 13 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 36
[5 empty] | 14 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 5 | 34
[5 empty] | 15 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 38
[5 empty] | 16 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 7 | 19
[5 empty] | 17 |  |  |  |  | 10 | 2 | 12 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 58
[5 empty] | 18 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[5 empty] | 19 |  |  |  |  | 8 | 2 | 10 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 42
[5 empty] | 20 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 42
[5 empty] | 21 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 8 | 59
[5 empty] | 22 |  |  |  |  | 11 | 0 | 11 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 6 | 42
[5 empty] | 23 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 5 | 56
[5 empty] | 24 |  |  |  |  | 9 | 2 | 11 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 20
[5 empty] | 25 |  |  |  |  | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 8 | 43
[5 empty] | 26 |  |  |  |  | 6 | 0 | 6 | 3 | 0 | 3 | 8 | 16 | 0 | 24 | 5 | 35
[5 empty] | 27 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 56
[5 empty] | 28 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 33
[5 empty] | 29 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 54
[5 empty] | 30 |  |  |  |  | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 8 | 59
[5 empty] | 31 |  |  |  |  | 6 | 0 | 6 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 4 | 32
[5 empty] | 32 |  |  |  |  | 8 | 0 | 8 | 6 | 0 | 6 | 4 | 0 | 0 | 4 | 9 | 21
[5 empty] | 33 |  |  |  |  | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 3 | 16
[5 empty] | 34 |  |  |  |  | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 6 | 40
[5 empty] | 35 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 6 | 17
[5 empty] | 36 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 19
[5 empty] | 37 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 8 | 57
[5 empty] | 38 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 20
[5 empty] | 39 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 21
[5 empty] | 40 |  |  |  |  | 7 | 0 | 7 | 5 | 0 | 5 | 6 | 16 | 20 | 42 | 6 | 55
[5 empty] | 41 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 33
[5 empty] | 42 |  |  |  |  | 10 | 0 | 10 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 7 | 36
[5 empty] | 43 |  |  |  |  | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 8 | 22
[5 empty] | 44 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 9 | 57
[5 empty] | 45 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 1 | 16 | 20 | 37 | 7 | 53
[5 empty] | 46 |  |  |  |  | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 54
[5 empty] | 47 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 8 | 23
[5 empty] | 48 |  |  |  |  | 6 | 2 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 34
[5 empty] | 49 |  |  |  |  | 8 | 0 | 8 | 3 | 9 | 12 | 7 | 16 | 0 | 23 | 7 | 38
[5 empty] | 50 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 37
[5 empty] | 51 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 6 | 53
[5 empty] | 52 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 55
[5 empty] | 53 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 5 | 32
[5 empty] | 54 |  |  |  |  | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 7 | 41
[5 empty] | 55 |  |  |  |  | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 6 | 41
[5 empty] | 56 |  |  |  |  | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 16 | 20 | 40 | 6 | 54
[5 empty] | 57 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[5 empty] | 58 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 56
[5 empty] | 59 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 33
[5 empty] | 60 |  |  |  |  | 10 | 0 | 10 | 7 | 0 | 7 | 5 | 16 | 0 | 21 | 7 | 38
[5 empty] | 61 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 6 | 53
[5 empty] | 62 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 18
[5 empty] | 63 |  |  |  |  | 10 | 0 | 10 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 6 | 19
[5 empty] | 64 |  |  |  |  | 9 | 0 | 9 | 2 | 9 | 11 | 6 | 0 | 20 | 26 | 4 | 39
[5 empty] | 65 |  |  |  |  | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 8 | 38
[5 empty] | 66 |  |  |  |  | 11 | 0 | 11 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 8 | 21
[5 empty] | 67 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 9 | 43
[5 empty] | 68 |  |  |  |  | 7 | 2 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 34
[5 empty] | 69 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 5 | 16
[5 empty] | 70 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 9 | 58
[5 empty] | 71 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 57
[5 empty] | 72 |  |  |  |  | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 55
[5 empty] | 73 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 20
[5 empty] | 74 |  |  |  |  | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 7 | 37
[5 empty] | 75 |  |  |  |  | 7 | 0 | 7 | 5 | 9 | 14 | 5 | 0 | 20 | 25 | 5 | 37
[5 empty] | 76 |  |  |  |  | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 54
[5 empty] | 77 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[5 empty] | 78 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 5 | 39
[5 empty] | 79 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 7 | 58
[5 empty] | 80 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 4 | 53
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 11 | 0 | 11 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 6 | 16 | 0 | 22 | 5 | 36
[10 empty] | 11 | 0 | 11 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 6 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 9 | 2 | 11 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 5 | 41
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 0 | 0 | 6 | 8 | 23
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 9 | 40
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 59
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 2 | 16 | 0 | 18 | 8 | 34
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 7 | 20
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 20
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 8 | 2 | 10 | 2 | 0 | 2 | 3 | 0 | 0 | 3 | 8 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 2 | 0 | 20 | 22 | 7 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 8 | 42
[10 empty] | 5 | 0 | 5 | 2 | 9 | 11 | 7 | 0 | 20 | 27 | 6 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 39
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 54
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 16
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 8 | 57
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 0 | 2 | 6 | 17
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 8 | 58
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 8 | 20
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 42
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 8 | 36
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 7 | 16 | 0 | 23 | 6 | 39
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 7 | 37
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 2 | 16 | 20 | 38 | 6 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 7 | 42
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 5 | 55
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 16 | 0 | 18 | 6 | 33
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 39
[10 empty] | 7 | 0 | 7 | 1 | 9 | 10 | 6 | 0 | 20 | 26 | 6 | 39
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 5 | 56
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 7 | 2 | 9 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 9 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 5 | 19
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 58
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 6 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 6 | 22
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 7 | 46
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 8 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 7 | 17
[10 empty] | 8 | 0 | 8 | 6 | 0 | 6 | 3 | 0 | 0 | 3 | 8 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 42
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 11 | 2 | 13 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 7 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 11 | 0 | 11 | 5 | 9 | 14 | 3 | 0 | 20 | 23 | 6 | 40
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 39
[10 empty] | 11 | 0 | 11 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 1 | 0 | 1 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 7 | 0 | 20 | 27 | 7 | 43
[10 empty] | 9 | 2 | 11 | 1 | 0 | 1 | 3 | 16 | 20 | 39 | 6 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 34
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 22
[10 empty] | 12 | 0 | 12 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 7 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 24
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 8 | 22
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 5 | 35
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 5 | 35
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 35
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 7 | 0 | 0 | 7 | 9 | 25
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 7 | 0 | 20 | 27 | 6 | 42
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 6 | 52
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 7 | 43
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 5 | 19
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 9 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 8 | 0 | 20 | 28 | 7 | 45
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 3 | 16 | 20 | 39 | 6 | 52
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 9 | 42
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 60
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 39
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 8 | 37
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 10 | 2 | 12 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 5 | 42
[10 empty] | 9 | 0 | 9 | 1 | 9 | 10 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 17
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 7 | 16 | 20 | 43 | 5 | 56
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 6 | 39
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 39
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 4 | 33
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 23
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 53
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 1 | 0 | 0 | 1 | 5 | 14
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 59
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 7 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 7 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 7 | 0 | 20 | 27 | 8 | 43
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 5 | 0 | 5 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 1 | 0 | 20 | 21 | 6 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 8 | 53
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 6 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 5 | 16 | 20 | 41 | 8 | 55
[10 empty] | 9 | 2 | 11 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 6 | 41
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 6 | 2 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 5 | 38
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 2 | 0 | 20 | 22 | 7 | 36
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 8 | 42
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 9 | 41
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 8 | 59
[10 empty] | 12 | 0 | 12 | 2 | 9 | 11 | 5 | 16 | 20 | 41 | 7 | 60
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 9 | 59
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 23
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 32
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 5 | 15
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 7 | 2 | 9 | 3 | 9 | 12 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 11 | 2 | 13 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 43
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 20
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 7 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 8 | 36
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 37
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 3 | 16 | 20 | 39 | 7 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 2 | 11 | 2 | 9 | 11 | 6 | 0 | 20 | 26 | 6 | 43
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 5 | 57
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 10 | 0 | 10 | 6 | 0 | 6 | 3 | 0 | 0 | 3 | 7 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 57
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 23
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 4 | 36
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 2 | 16 | 20 | 38 | 6 | 54
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 5 | 30
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 55
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 7 | 25
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 7 | 0 | 0 | 7 | 8 | 25
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 59
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 23
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 8 | 22
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 56
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 41
[10 empty] | 12 | 0 | 12 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 24
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 7 | 0 | 20 | 27 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 40
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 39
[10 empty] | 8 | 2 | 10 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 9 | 25
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 4 | 33
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 7 | 18
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 7 | 16 | 0 | 23 | 9 | 43
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 12 | 0 | 12 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 6 | 61
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 8 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 11 | 2 | 13 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 6 | 61
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 5 | 15
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 7 | 59
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 35
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 58
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 7 | 16 | 0 | 23 | 8 | 39
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 8 | 55
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 7 | 18
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 7 | 54
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 22
[10 empty] | 6 | 2 | 8 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 8 | 42
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 5 | 56
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 40
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 6 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 4 | 37
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 5 | 41
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 7 | 58
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 7 | 53
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 6 | 17
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 5 | 18
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 9 | 59
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 9 | 45
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 33
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 8 | 23
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 7 | 2 | 9 | 5 | 9 | 14 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 5 | 0 | 5 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 37
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 8 | 24
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 5 | 0 | 5 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 50
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 5 | 36
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 7 | 44
[10 empty] | 7 | 2 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 5 | 18
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 6 | 59
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 5 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 0 | 20 | 22 | 8 | 39
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 8 | 60
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 24
[10 empty] | 7 | 2 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 34
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 6 | 23
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 5 | 15
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 7 | 60
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 6 | 37
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 0 | 2 | 7 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 5 | 35
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 7 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 8 | 16 | 20 | 44 | 7 | 59
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 7 | 16 | 0 | 23 | 7 | 41
[10 empty] | 7 | 0 | 7 | 1 | 0 | 1 | 4 | 0 | 0 | 4 | 8 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 6 | 53
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 21
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 43
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 55
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 10 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 6 | 20
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 5 | 17
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 20
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 22
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 2 | 16 | 20 | 38 | 7 | 53
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 8 | 2 | 10 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 7 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 5 | 32
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 7 | 37
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 9 | 63
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 31
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 54
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 5 | 34
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 56
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 9 | 57
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 51
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 8 | 56
[10 empty] | 10 | 2 | 12 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 5 | 57
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 6 | 22
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 32
[10 empty] | 5 | 0 | 5 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 7 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 7 | 58
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 20 | 23 | 9 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 6 | 52
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 1 | 16 | 0 | 17 | 8 | 35
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 20
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 6 | 43
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 5 | 38
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 9 | 36
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 7 | 35
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 43
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 7 | 42
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 21
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 5 | 41
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 6 | 22
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 38
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 6 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 42
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 55
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 8 | 0 | 8 | 1 | 9 | 10 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 20
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 5 | 33
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 7 | 16 | 0 | 23 | 6 | 36
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 34
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 8 | 0 | 0 | 8 | 4 | 20
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 59
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 8 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 6 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 5 | 36
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 4 | 33
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 1 | 16 | 0 | 17 | 8 | 35
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 7 | 44
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 10 | 0 | 10 | 5 | 9 | 14 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 10 | 43
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 5 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 5 | 16
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 7 | 32
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 5 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 9 | 42
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 20
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 9 | 24
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 0 | 0 | 6 | 8 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 6 | 57
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 8 | 23
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 5 | 56
[10 empty] | 12 | 0 | 12 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 7 | 39
[10 empty] | 7 | 2 | 9 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 10 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 4 | 49
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 4 | 50
[10 empty] | 10 | 2 | 12 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 7 | 22
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 4 | 33
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 55
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 2 | 16 | 0 | 18 | 8 | 35
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 14
[10 empty] | 9 | 2 | 11 | 2 | 9 | 11 | 5 | 0 | 20 | 25 | 7 | 43
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 8 | 57
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 5 | 39
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 6 | 16 | 0 | 22 | 6 | 34
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 8 | 20
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 17
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 6 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 58
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 6 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 10 | 2 | 12 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 42
[10 empty] | 11 | 2 | 13 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 61
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 2 | 11 | 5 | 9 | 14 | 3 | 0 | 0 | 3 | 6 | 20
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 16 | 0 | 22 | 10 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 7 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 59
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 43
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 3 | 15
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 41
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 35
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 5 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 0 | 2 | 8 | 19
[10 empty] | 12 | 0 | 12 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 8 | 43
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 6 | 2 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 5 | 38
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 8 | 56
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 9 | 19
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 5 | 0 | 5 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 32
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 34
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 22
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 5 | 36
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 7 | 20
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 52
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 5 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 57
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 9 | 42
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 41
[10 empty] | 9 | 2 | 11 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 5 | 36
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 4 | 19
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 6 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 5 | 52
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 8 | 16 | 0 | 24 | 6 | 39
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 3 | 0 | 20 | 23 | 7 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 5 | 55
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 3 | 16 | 0 | 19 | 7 | 33
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 42
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 22
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 58
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 7 | 42
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 8 | 39
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 7 | 16 | 20 | 43 | 6 | 56
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 9 | 46
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 7 | 34
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 5 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 9 | 56
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 2 | 16 | 20 | 38 | 7 | 52
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 5 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 44
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 6 | 16
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 55
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 6 | 2 | 8 | 2 | 9 | 11 | 3 | 16 | 0 | 19 | 7 | 34
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 23
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 54
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 7 | 35
[10 empty] | 10 | 2 | 12 | 3 | 9 | 12 | 8 | 16 | 20 | 44 | 6 | 62
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 57
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 10 | 2 | 12 | 5 | 9 | 14 | 5 | 16 | 0 | 21 | 6 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 7 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 58
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 55
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 37
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 7 | 38
[10 empty] | 7 | 0 | 7 | 1 | 9 | 10 | 6 | 0 | 0 | 6 | 10 | 23
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 5 | 19
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 36
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 5 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 0 | 20 | 22 | 7 | 38
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 20 | 23 | 8 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 56
[10 empty] | 11 | 2 | 13 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 61
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 9 | 46
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 5 | 34
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 36
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 5 | 35
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 7 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 8 | 40
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 39
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 8 | 43
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 4 | 0 | 0 | 4 | 9 | 22
[10 empty] | 6 | 0 | 6 | 2 | 9 | 11 | 4 | 0 | 0 | 4 | 7 | 17
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 11 | 0 | 11 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 6 | 40
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 7 | 16 | 20 | 43 | 8 | 61
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 17
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 5 | 16
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 8 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 7 | 55
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 4 | 16 | 20 | 40 | 6 | 52
[10 empty] | 11 | 2 | 13 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 40
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 8 | 22
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 7 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 4 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 8 | 23
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 10 | 59
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 8 | 56
[10 empty] | 5 | 0 | 5 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 32
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 8 | 59
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 4 | 17
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 38
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 7 | 16 | 0 | 23 | 6 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 4 | 33
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 8 | 2 | 10 | 3 | 9 | 12 | 3 | 0 | 0 | 3 | 7 | 20
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 6 | 40
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 7 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 4 | 52
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 11 | 2 | 13 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 7 | 25
[10 empty] | 6 | 0 | 6 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 7 | 33
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 7 | 0 | 0 | 7 | 7 | 21
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 8 | 0 | 20 | 28 | 4 | 42
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 18
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 6 | 16 | 20 | 42 | 7 | 59
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 19
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 7 | 2 | 9 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 6 | 35
[10 empty] | 8 | 0 | 8 | 1 | 9 | 10 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 12 | 0 | 12 | 5 | 9 | 14 | 3 | 0 | 0 | 3 | 5 | 20
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 5 | 37
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 8 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 6 | 35
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 40
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 7 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 8 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 5 | 53
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 8 | 39
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 16 | 0 | 19 | 7 | 35
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 7 | 16 | 0 | 23 | 9 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 17
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 5 | 53
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 6 | 42
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 57
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 42
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 54
[10 empty] | 10 | 2 | 12 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 7 | 43
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 6 | 23
[10 empty] | 10 | 2 | 12 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 7 | 41
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 5 | 52
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 5 | 34
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 34
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 8 | 40
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 58
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 6 | 50
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 8 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 6 | 39
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 7 | 21
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 5 | 53
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 4 | 38
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 57
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 42
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 17
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 40
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 0 | 2 | 8 | 19
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 7 | 40
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 1 | 0 | 0 | 1 | 8 | 19
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 8 | 59
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 5 | 0 | 0 | 5 | 7 | 22
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 40
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 8 | 2 | 10 | 2 | 9 | 11 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 2 | 0 | 20 | 22 | 5 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 17
[10 empty] | 11 | 2 | 13 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 6 | 62
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 6 | 20
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 0 | 0 | 4 | 8 | 20
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 38
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 8 | 0 | 8 | 6 | 0 | 6 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 3 | 0 | 20 | 23 | 6 | 39
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 36
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 5 | 42
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 58
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 5 | 0 | 5 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 8 | 36
[9 empty] | Average |  |  | 8.725 |  |  | 5.436 |  |  |  | 23.658 | 6.554 | 38.937
[9 empty] | Std |  |  | 1.399 |  |  | 3.8446 |  |  |  | 12.4253 | 1.1119 | 12.5547

## Critical Path Distribution
Duration | Frequency | Cumulative %
1 | 0 | 0%
2 | 0 | 0%
3 | 0 | 0%
4 | 0 | 0%
5 | 0 | 0%
6 | 0 | 0%
7 | 0 | 0%
8 | 0 | 0%
9 | 0 | 0%
10 | 0 | 0%
11 | 0 | 0%
12 | 0 | 0%
13 | 0 | 0%
14 | 1 | 0.1%
15 | 5 | 0.6%
16 | 15 | 2.1%
17 | 27 | 4.8%
18 | 47 | 9.5%
19 | 44 | 13.9%
20 | 49 | 18.8%
21 | 41 | 22.9%
22 | 28 | 25.7%
23 | 14 | 27.1%
24 | 6 | 27.7%
25 | 2 | 27.9%
26 | 3 | 28.2%
27 | 0 | 28.2%
28 | 0 | 28.2%
29 | 2 | 28.4%
30 | 0 | 28.4%
31 | 1 | 28.5%
32 | 12 | 29.7%
33 | 18 | 31.5%
34 | 27 | 34.2%
35 | 52 | 39.4%
36 | 54 | 44.8%
37 | 55 | 50.3%
38 | 59 | 56.2%
39 | 61 | 62.3%
40 | 49 | 67.2%
41 | 31 | 70.3%
42 | 20 | 72.3%
43 | 15 | 73.8%
44 | 3 | 74.1%
45 | 2 | 74.3%
46 | 0 | 74.3%
47 | 0 | 74.3%
48 | 0 | 74.3%
49 | 0 | 74.3%
50 | 2 | 74.5%
51 | 6 | 75.1%
52 | 16 | 76.7%
53 | 15 | 78.2%
54 | 36 | 81.8%
55 | 44 | 86.2%
56 | 45 | 90.7%
57 | 40 | 94.7%
58 | 23 | 97%
59 | 17 | 98.7%
60 | 8 | 99.5%
61 | 3 | 99.8%
62 | 2 | 100%
63 | 0 | 100%
64 | 0 | 100%
65 | 0 | 100%
66 | 0 | 100%
67 | 0 | 100%
68 | 0 | 100%
69 | 0 | 100%
70 | 0 | 100%
71 | 0 | 100%
72 | 0 | 100%
73 | 0 | 100%
74 | 0 | 100%
75 | 0 | 100%
76 | 0 | 100%
77 | 0 | 100%
78 | 0 | 100%
79 | 0 | 100%
80 | 0 | 100%
More | 0 | 100%

## Critical Path Dist Data
Task Number | Optimistic | Most Likely | Pessimistic | Average | Standard Deviation | Risk Event Probability | Risk Event | Risk Event Impact (Days) |  | Task 1 Value | Risk 1 Value | Total Task 1 | Task 2 Value | Risk 2 Value | Total Task 2 | Task 3 Value | Risk 3 Value | Risk 4 Value | Total Task 3 | Task 4 Value | Critical Path Total T1,T3,T4
Task 1 | 6 | 9 | 12 | 9 | 1.2247 | 10% | R1 | 2 |  | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 6 | 38
Task 2 | 2 | 4 | 6 | 4 | 0.8165 | 25% | R4 | 9 |  | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 6 | 37
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R2 | 16 |  | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 5 | 38
Task 3 | 2 | 5 | 8 | 5 | 1.2247 | 50% | R3 | 20 |  | 6 | 0 | 6 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 7 | 32
Task 4 | 4 | 8 | 9 | 7 | 1.0801 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[5 empty] | Duration |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 5 | 19
[5 empty] | 1 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 6 | 40
[5 empty] | 2 |  |  |  |  | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 39
[5 empty] | 3 |  |  |  |  | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 4 | 54
[5 empty] | 4 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 39
[5 empty] | 5 |  |  |  |  | 9 | 2 | 11 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 8 | 39
[5 empty] | 6 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 3 | 51
[5 empty] | 7 |  |  |  |  | 11 | 0 | 11 | 3 | 9 | 12 | 7 | 16 | 20 | 43 | 5 | 59
[5 empty] | 8 |  |  |  |  | 8 | 2 | 10 | 6 | 0 | 6 | 6 | 16 | 0 | 22 | 8 | 40
[5 empty] | 9 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 38
[5 empty] | 10 |  |  |  |  | 6 | 0 | 6 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 52
[5 empty] | 11 |  |  |  |  | 8 | 2 | 10 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 7 | 56
[5 empty] | 12 |  |  |  |  | 10 | 0 | 10 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 6 | 19
[5 empty] | 13 |  |  |  |  | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 4 | 55
[5 empty] | 14 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 34
[5 empty] | 15 |  |  |  |  | 8 | 0 | 8 | 3 | 9 | 12 | 2 | 0 | 0 | 2 | 6 | 16
[5 empty] | 16 |  |  |  |  | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 8 | 59
[5 empty] | 17 |  |  |  |  | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 4 | 19
[5 empty] | 18 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 8 | 57
[5 empty] | 19 |  |  |  |  | 6 | 0 | 6 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 5 | 37
[5 empty] | 20 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 38
[5 empty] | 21 |  |  |  |  | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 8 | 39
[5 empty] | 22 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 39
[5 empty] | 23 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 56
[5 empty] | 24 |  |  |  |  | 7 | 2 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 39
[5 empty] | 25 |  |  |  |  | 10 | 2 | 12 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 5 | 58
[5 empty] | 26 |  |  |  |  | 9 | 2 | 11 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 8 | 22
[5 empty] | 27 |  |  |  |  | 7 | 0 | 7 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 7 | 56
[5 empty] | 28 |  |  |  |  | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 20
[5 empty] | 29 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 33
[5 empty] | 30 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 9 | 42
[5 empty] | 31 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 43
[5 empty] | 32 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 56
[5 empty] | 33 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 5 | 35
[5 empty] | 34 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 9 | 38
[5 empty] | 35 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 20
[5 empty] | 36 |  |  |  |  | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 6 | 38
[5 empty] | 37 |  |  |  |  | 5 | 0 | 5 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 15
[5 empty] | 38 |  |  |  |  | 8 | 2 | 10 | 4 | 9 | 13 | 7 | 0 | 20 | 27 | 7 | 44
[5 empty] | 39 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 6 | 34
[5 empty] | 40 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 8 | 40
[5 empty] | 41 |  |  |  |  | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 5 | 19
[5 empty] | 42 |  |  |  |  | 8 | 0 | 8 | 5 | 0 | 5 | 7 | 16 | 0 | 23 | 6 | 37
[5 empty] | 43 |  |  |  |  | 10 | 0 | 10 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 7 | 22
[5 empty] | 44 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 17
[5 empty] | 45 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 20
[5 empty] | 46 |  |  |  |  | 10 | 0 | 10 | 2 | 9 | 11 | 4 | 0 | 0 | 4 | 8 | 22
[5 empty] | 47 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 36
[5 empty] | 48 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 5 | 52
[5 empty] | 49 |  |  |  |  | 5 | 0 | 5 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 38
[5 empty] | 50 |  |  |  |  | 8 | 2 | 10 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 7 | 41
[5 empty] | 51 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[5 empty] | 52 |  |  |  |  | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 6 | 56
[5 empty] | 53 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 21
[5 empty] | 54 |  |  |  |  | 10 | 0 | 10 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 5 | 38
[5 empty] | 55 |  |  |  |  | 10 | 0 | 10 | 5 | 0 | 5 | 1 | 0 | 20 | 21 | 7 | 38
[5 empty] | 56 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 23
[5 empty] | 57 |  |  |  |  | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 6 | 40
[5 empty] | 58 |  |  |  |  | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 19
[5 empty] | 59 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[5 empty] | 60 |  |  |  |  | 8 | 2 | 10 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 21
[5 empty] | 61 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 37
[5 empty] | 62 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 4 | 52
[5 empty] | 63 |  |  |  |  | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 38
[5 empty] | 64 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 7 | 36
[5 empty] | 65 |  |  |  |  | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 33
[5 empty] | 66 |  |  |  |  | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 5 | 18
[5 empty] | 67 |  |  |  |  | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 41
[5 empty] | 68 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 5 | 34
[5 empty] | 69 |  |  |  |  | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 5 | 19
[5 empty] | 70 |  |  |  |  | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[5 empty] | 71 |  |  |  |  | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 56
[5 empty] | 72 |  |  |  |  | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 41
[5 empty] | 73 |  |  |  |  | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 8 | 58
[5 empty] | 74 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 19
[5 empty] | 75 |  |  |  |  | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 20
[5 empty] | 76 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 5 | 38
[5 empty] | 77 |  |  |  |  | 7 | 2 | 9 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 8 | 20
[5 empty] | 78 |  |  |  |  | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 33
[5 empty] | 79 |  |  |  |  | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 20
[5 empty] | 80 |  |  |  |  | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 9 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 7 | 23
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 6 | 39
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 6 | 21
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 8 | 19
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 36
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 5 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 7 | 34
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 17
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 4 | 51
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 17
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 38
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 8 | 55
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 4 | 34
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 8 | 60
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 10 | 2 | 12 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 6 | 22
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 6 | 17
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 8 | 2 | 10 | 2 | 9 | 11 | 3 | 16 | 20 | 39 | 9 | 58
[10 empty] | 8 | 2 | 10 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 3 | 16 | 0 | 19 | 6 | 32
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 16 | 0 | 19 | 7 | 35
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 8 | 38
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 5 | 0 | 5 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 38
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 4 | 32
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 5 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 10 | 2 | 12 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 57
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 20
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 4 | 17
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 6 | 20
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 21
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 3 | 0 | 0 | 3 | 7 | 20
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 8 | 60
[10 empty] | 10 | 0 | 10 | 5 | 9 | 14 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 5 | 52
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 7 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 8 | 36
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 7 | 17
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 6 | 19
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 51
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 7 | 39
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 8 | 40
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 2 | 0 | 20 | 22 | 6 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 15
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 7 | 39
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 2 | 10 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 22
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 7 | 59
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 9 | 43
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 3 | 16 | 0 | 19 | 6 | 32
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 2 | 0 | 0 | 2 | 8 | 18
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 34
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 8 | 22
[10 empty] | 12 | 0 | 12 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 7 | 44
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 6 | 18
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 6 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 9 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 8 | 42
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 0 | 7 | 4 | 18
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 6 | 23
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 4 | 31
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 7 | 58
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 8 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 20 | 27 | 6 | 41
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 35
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 8 | 54
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 8 | 39
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 2 | 0 | 0 | 2 | 7 | 17
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 7 | 34
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 35
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 7 | 16 | 0 | 23 | 8 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 22
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 8 | 16 | 20 | 44 | 7 | 59
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 5 | 52
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 32
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 0 | 0 | 6 | 6 | 19
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 9 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 6 | 16
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 31
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 2 | 0 | 20 | 22 | 7 | 38
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 7 | 21
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 2 | 0 | 20 | 22 | 6 | 34
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 1 | 0 | 20 | 21 | 8 | 37
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 36
[10 empty] | 9 | 2 | 11 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 57
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 1 | 16 | 0 | 17 | 8 | 33
[10 empty] | 8 | 0 | 8 | 6 | 0 | 6 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 5 | 16 | 0 | 21 | 6 | 33
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 6 | 35
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 4 | 19
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 20
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 6 | 36
[10 empty] | 10 | 2 | 12 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 4 | 56
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 37
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 4 | 0 | 0 | 4 | 6 | 17
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 5 | 39
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 8 | 42
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 20
[10 empty] | 12 | 2 | 14 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 25
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 0 | 0 | 6 | 6 | 22
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 8 | 16 | 0 | 24 | 5 | 37
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 24
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 7 | 16 | 20 | 43 | 8 | 59
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 7 | 53
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 36
[10 empty] | 7 | 2 | 9 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 22
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 7 | 45
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 6 | 16
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 9 | 23
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 12 | 2 | 14 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 46
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 40
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 2 | 16 | 20 | 38 | 6 | 53
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 5 | 0 | 20 | 25 | 7 | 38
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 9 | 57
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 6 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 9 | 22
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 42
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 16 | 20 | 39 | 7 | 54
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 42
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 4 | 17
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 6 | 21
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 10 | 24
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 8 | 40
[10 empty] | 9 | 2 | 11 | 2 | 9 | 11 | 7 | 16 | 20 | 43 | 4 | 58
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 8 | 21
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 10 | 0 | 10 | 6 | 0 | 6 | 6 | 0 | 20 | 26 | 8 | 44
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 8 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 5 | 53
[10 empty] | 12 | 0 | 12 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 24
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 5 | 36
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 7 | 0 | 20 | 27 | 7 | 41
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 4 | 56
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 8 | 20
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 4 | 34
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 8 | 59
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 35
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 3 | 52
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 2 | 16 | 20 | 38 | 7 | 53
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 9 | 0 | 0 | 9 | 6 | 23
[10 empty] | 6 | 0 | 6 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 7 | 33
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 5 | 19
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 53
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 8 | 59
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 33
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 7 | 16 | 20 | 43 | 5 | 56
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 0 | 0 | 6 | 9 | 25
[10 empty] | 12 | 0 | 12 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 6 | 39
[10 empty] | 5 | 2 | 7 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 9 | 41
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 5 | 36
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 40
[10 empty] | 9 | 2 | 11 | 5 | 9 | 14 | 5 | 16 | 0 | 21 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 16
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 36
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 10 | 2 | 12 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 43
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 53
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 7 | 21
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 23
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 35
[10 empty] | 10 | 0 | 10 | 5 | 9 | 14 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 6 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 5 | 36
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 6 | 20
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 5 | 17
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 6 | 58
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 5 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 6 | 20
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 2 | 0 | 0 | 2 | 6 | 16
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 8 | 53
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 5 | 37
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 20 | 23 | 7 | 39
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 16 | 0 | 22 | 8 | 39
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 55
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 8 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 8 | 43
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 7 | 59
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 6 | 32
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 9 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 3 | 0 | 20 | 23 | 6 | 37
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 6 | 16 | 0 | 22 | 8 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 8 | 0 | 8 | 1 | 0 | 1 | 2 | 16 | 20 | 38 | 5 | 51
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 8 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 8 | 22
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 58
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 5 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 5 | 36
[10 empty] | 10 | 0 | 10 | 5 | 9 | 14 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 4 | 0 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 14
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 7 | 43
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 4 | 54
[10 empty] | 10 | 2 | 12 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 38
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 8 | 0 | 0 | 8 | 7 | 23
[10 empty] | 7 | 2 | 9 | 2 | 9 | 11 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 8 | 42
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 55
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 10 | 40
[10 empty] | 7 | 2 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 8 | 43
[10 empty] | 8 | 2 | 10 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 6 | 40
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 41
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 2 | 0 | 0 | 2 | 4 | 13
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 0 | 0 | 3 | 8 | 20
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 6 | 35
[10 empty] | 7 | 2 | 9 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 8 | 59
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 4 | 36
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 59
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 39
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 8 | 16 | 0 | 24 | 6 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 6 | 36
[10 empty] | 8 | 2 | 10 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 7 | 55
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 7 | 18
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 7 | 36
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 7 | 37
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 41
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 2 | 0 | 0 | 2 | 7 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 8 | 38
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 43
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 8 | 38
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 8 | 58
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 8 | 57
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 32
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 43
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 4 | 19
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 8 | 39
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 6 | 0 | 20 | 26 | 8 | 42
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 4 | 0 | 20 | 24 | 6 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 9 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 0 | 20 | 5 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 8 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 8 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 9 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 5 | 17
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 8 | 2 | 10 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 8 | 38
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 5 | 55
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 8 | 16 | 0 | 24 | 4 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 8 | 0 | 20 | 28 | 6 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 16 | 0 | 19 | 8 | 35
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 7 | 20
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 8 | 37
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 2 | 0 | 20 | 22 | 6 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 5 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 6 | 15
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 6 | 37
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 9 | 57
[10 empty] | 7 | 0 | 7 | 2 | 9 | 11 | 4 | 0 | 20 | 24 | 8 | 39
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 39
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 55
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 6 | 0 | 0 | 6 | 6 | 19
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 19
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 6 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 6 | 32
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 6 | 16
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 0 | 20 | 22 | 5 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 8 | 58
[10 empty] | 10 | 2 | 12 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 23
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 8 | 37
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 6 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 8 | 36
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 5 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 20 | 42 | 5 | 55
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 39
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 9 | 59
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 21
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 58
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 8 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 5 | 39
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 23
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 6 | 42
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 7 | 0 | 20 | 27 | 9 | 44
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 58
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 13
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 39
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 23
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 7 | 56
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 20
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 8 | 38
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 8 | 39
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 6 | 0 | 0 | 6 | 8 | 24
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 7 | 0 | 20 | 27 | 7 | 42
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 7 | 16
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 43
[10 empty] | 10 | 2 | 12 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 38
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 23
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 2 | 16 | 0 | 18 | 4 | 31
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 5 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 37
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 5 | 0 | 0 | 5 | 6 | 18
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 5 | 36
[10 empty] | 8 | 2 | 10 | 5 | 9 | 14 | 4 | 0 | 0 | 4 | 7 | 21
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 8 | 44
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 6 | 38
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 1 | 16 | 0 | 17 | 8 | 33
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 8 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 3 | 53
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 7 | 2 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 20
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 58
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 5 | 0 | 0 | 5 | 7 | 20
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 5 | 19
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 35
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 36
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 42
[10 empty] | 6 | 2 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 11 | 0 | 11 | 5 | 0 | 5 | 4 | 16 | 20 | 40 | 8 | 59
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 7 | 0 | 7 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 8 | 56
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 8 | 58
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 17
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 2 | 0 | 20 | 22 | 8 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 56
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 7 | 22
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 20
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 12 | 0 | 12 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 24
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 7 | 18
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 7 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 11 | 0 | 11 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 7 | 42
[10 empty] | 8 | 2 | 10 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 7 | 59
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 38
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 5 | 55
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 8 | 2 | 10 | 4 | 9 | 13 | 7 | 0 | 0 | 7 | 5 | 22
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 7 | 22
[10 empty] | 9 | 2 | 11 | 2 | 9 | 11 | 5 | 0 | 20 | 25 | 8 | 44
[10 empty] | 7 | 2 | 9 | 5 | 0 | 5 | 8 | 16 | 0 | 24 | 9 | 42
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 8 | 0 | 8 | 1 | 9 | 10 | 4 | 16 | 0 | 20 | 5 | 33
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 9 | 59
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 4 | 54
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 23
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 8 | 57
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 6 | 23
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 6 | 0 | 6 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 8 | 34
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 7 | 0 | 7 | 1 | 0 | 1 | 6 | 0 | 20 | 26 | 7 | 40
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 7 | 17
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 20 | 22 | 6 | 36
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 19
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 52
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 5 | 33
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 24
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 0 | 0 | 6 | 6 | 22
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 8 | 22
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 6 | 19
[10 empty] | 9 | 2 | 11 | 2 | 9 | 11 | 4 | 16 | 0 | 20 | 7 | 38
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 5 | 35
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 3 | 16 | 0 | 19 | 7 | 32
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 2 | 10 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 6 | 2 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 4 | 16 | 0 | 20 | 5 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 9 | 39
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 8 | 55
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 7 | 56
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 7 | 0 | 20 | 27 | 5 | 39
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 8 | 40
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 21
[10 empty] | 7 | 2 | 9 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 1 | 0 | 0 | 1 | 5 | 16
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 2 | 0 | 0 | 2 | 8 | 20
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 6 | 2 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 17
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 6 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 7 | 0 | 7 | 1 | 0 | 1 | 8 | 0 | 20 | 28 | 6 | 41
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 7 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 6 | 16
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 5 | 37
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 22
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 8 | 21
[10 empty] | 7 | 2 | 9 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 7 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 4 | 50
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 8 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 16 | 20 | 43 | 8 | 59
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 37
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 22
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 9 | 0 | 20 | 29 | 5 | 45
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 4 | 53
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 38
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 7 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 10 | 0 | 10 | 1 | 0 | 1 | 4 | 16 | 0 | 20 | 5 | 35
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 3 | 16 | 20 | 39 | 7 | 54
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 7 | 16 | 0 | 23 | 8 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 41
[10 empty] | 9 | 0 | 9 | 5 | 9 | 14 | 2 | 0 | 0 | 2 | 7 | 18
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 5 | 39
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 6 | 55
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 37
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 6 | 0 | 0 | 6 | 7 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 8 | 37
[10 empty] | 13 | 0 | 13 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 43
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 37
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 2 | 16 | 0 | 18 | 5 | 33
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 5 | 32
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 4 | 0 | 0 | 4 | 5 | 17
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 0 | 21 | 4 | 32
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 9 | 60
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 2 | 16 | 0 | 18 | 7 | 32
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 53
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 0 | 20 | 26 | 6 | 42
[10 empty] | 8 | 2 | 10 | 3 | 9 | 12 | 6 | 16 | 0 | 22 | 8 | 40
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 6 | 56
[10 empty] | 10 | 0 | 10 | 2 | 0 | 2 | 6 | 0 | 20 | 26 | 5 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 6 | 35
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 8 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 7 | 16 | 20 | 43 | 8 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 7 | 36
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 7 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 6 | 54
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 6 | 23
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 41
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 7 | 57
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 2 | 0 | 0 | 2 | 4 | 14
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 6 | 22
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 3 | 16 | 0 | 19 | 5 | 33
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 52
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 37
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 8 | 41
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 8 | 41
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 2 | 11 | 3 | 0 | 3 | 1 | 16 | 0 | 17 | 7 | 35
[10 empty] | 6 | 0 | 6 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 8 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 7 | 20
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 21
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 0 | 4 | 8 | 20
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 2 | 16 | 0 | 18 | 8 | 33
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 3 | 16 | 20 | 39 | 7 | 56
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 7 | 38
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 6 | 0 | 6 | 5 | 9 | 14 | 3 | 16 | 20 | 39 | 7 | 52
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 6 | 20
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 53
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 11 | 0 | 11 | 4 | 9 | 13 | 3 | 0 | 20 | 23 | 6 | 40
[10 empty] | 7 | 2 | 9 | 5 | 0 | 5 | 4 | 0 | 20 | 24 | 7 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 7 | 22
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 6 | 37
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 8 | 0 | 8 | 2 | 9 | 11 | 1 | 0 | 0 | 1 | 7 | 16
[10 empty] | 10 | 0 | 10 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 7 | 58
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 20 | 41 | 5 | 55
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 58
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 5 | 34
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 40
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 35
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 2 | 16 | 20 | 38 | 5 | 49
[10 empty] | 7 | 0 | 7 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 7 | 53
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 5 | 51
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 8 | 20
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 20
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 6 | 53
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 4 | 35
[10 empty] | 6 | 0 | 6 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 6 | 51
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 6 | 16 | 0 | 22 | 6 | 37
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 7 | 20
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 5 | 16 | 20 | 41 | 7 | 59
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 5 | 13
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 8 | 42
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 6 | 0 | 0 | 6 | 6 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 7 | 21
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 39
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 7 | 23
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 4 | 0 | 0 | 4 | 8 | 20
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 5 | 54
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 2 | 0 | 0 | 2 | 5 | 16
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 56
[10 empty] | 11 | 0 | 11 | 3 | 9 | 12 | 3 | 16 | 20 | 39 | 8 | 58
[10 empty] | 7 | 2 | 9 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 6 | 0 | 6 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 52
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 6 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 0 | 22 | 7 | 38
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 6 | 58
[10 empty] | 8 | 0 | 8 | 5 | 9 | 14 | 3 | 16 | 0 | 19 | 6 | 33
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 4 | 34
[10 empty] | 10 | 0 | 10 | 2 | 9 | 11 | 3 | 0 | 0 | 3 | 7 | 20
[10 empty] | 6 | 0 | 6 | 4 | 9 | 13 | 6 | 16 | 20 | 42 | 8 | 56
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 3 | 0 | 20 | 23 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 16 | 0 | 21 | 7 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 55
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 41
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 3 | 16 | 0 | 19 | 5 | 30
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 7 | 16 | 0 | 23 | 7 | 39
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 7 | 0 | 0 | 7 | 7 | 22
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 5 | 18
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 5 | 40
[10 empty] | 9 | 2 | 11 | 5 | 0 | 5 | 3 | 0 | 20 | 23 | 6 | 40
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 3 | 36
[10 empty] | 10 | 0 | 10 | 4 | 9 | 13 | 5 | 0 | 0 | 5 | 8 | 23
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 5 | 54
[10 empty] | 9 | 2 | 11 | 2 | 0 | 2 | 3 | 16 | 20 | 39 | 5 | 55
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 5 | 16 | 0 | 21 | 6 | 33
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 4 | 0 | 0 | 4 | 6 | 18
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 7 | 0 | 20 | 27 | 5 | 40
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 3 | 0 | 20 | 23 | 7 | 37
[10 empty] | 6 | 2 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 20
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 5 | 53
[10 empty] | 6 | 0 | 6 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 8 | 19
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 33
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 2 | 0 | 0 | 2 | 5 | 15
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 8 | 21
[10 empty] | 8 | 2 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 5 | 15
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 6 | 38
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 5 | 52
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 7 | 0 | 7 | 5 | 9 | 14 | 3 | 0 | 0 | 3 | 5 | 15
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 0 | 20 | 25 | 7 | 42
[10 empty] | 6 | 0 | 6 | 3 | 9 | 12 | 3 | 0 | 20 | 23 | 8 | 37
[10 empty] | 7 | 0 | 7 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 7 | 34
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 8 | 42
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 4 | 16 | 20 | 40 | 9 | 58
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 0 | 20 | 6 | 34
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 6 | 40
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 16 | 20 | 42 | 7 | 57
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 16 | 20 | 39 | 7 | 55
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 7 | 16 | 0 | 23 | 9 | 42
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 6 | 0 | 20 | 26 | 6 | 43
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 6 | 2 | 8 | 2 | 0 | 2 | 4 | 16 | 20 | 40 | 7 | 55
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 7 | 20
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 7 | 0 | 0 | 7 | 9 | 24
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 4 | 0 | 20 | 24 | 5 | 38
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 54
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 7 | 56
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 4 | 0 | 20 | 24 | 6 | 39
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 4 | 16 | 0 | 20 | 6 | 35
[10 empty] | 8 | 0 | 8 | 2 | 0 | 2 | 6 | 16 | 20 | 42 | 6 | 56
[10 empty] | 8 | 0 | 8 | 4 | 9 | 13 | 4 | 0 | 20 | 24 | 5 | 37
[10 empty] | 11 | 0 | 11 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 8 | 60
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 6 | 54
[10 empty] | 7 | 2 | 9 | 4 | 9 | 13 | 7 | 16 | 20 | 43 | 9 | 61
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 0 | 16 | 20 | 36 | 6 | 51
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 5 | 0 | 20 | 25 | 6 | 41
[10 empty] | 9 | 0 | 9 | 4 | 9 | 13 | 3 | 0 | 0 | 3 | 6 | 18
[10 empty] | 10 | 0 | 10 | 5 | 9 | 14 | 5 | 0 | 0 | 5 | 6 | 21
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 6 | 20
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 16 | 0 | 21 | 7 | 36
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 7 | 35
[10 empty] | 13 | 0 | 13 | 2 | 0 | 2 | 3 | 16 | 0 | 19 | 8 | 40
[10 empty] | 9 | 0 | 9 | 2 | 0 | 2 | 5 | 16 | 0 | 21 | 6 | 36
[10 empty] | 11 | 0 | 11 | 3 | 0 | 3 | 4 | 16 | 20 | 40 | 6 | 57
[10 empty] | 11 | 0 | 11 | 3 | 9 | 12 | 5 | 16 | 20 | 41 | 8 | 60
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 37
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 5 | 16 | 20 | 41 | 7 | 57
[10 empty] | 12 | 0 | 12 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 8 | 23
[10 empty] | 8 | 2 | 10 | 4 | 0 | 4 | 4 | 16 | 0 | 20 | 6 | 36
[10 empty] | 8 | 0 | 8 | 3 | 0 | 3 | 5 | 0 | 0 | 5 | 5 | 18
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 16 | 20 | 42 | 6 | 57
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 10 | 0 | 10 | 3 | 9 | 12 | 4 | 16 | 20 | 40 | 5 | 55
[10 empty] | 10 | 0 | 10 | 4 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 19
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 20 | 39 | 8 | 56
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 8 | 56
[10 empty] | 8 | 0 | 8 | 3 | 9 | 12 | 6 | 0 | 20 | 26 | 7 | 41
[10 empty] | 9 | 0 | 9 | 3 | 9 | 12 | 3 | 16 | 0 | 19 | 6 | 34
[10 empty] | 11 | 0 | 11 | 5 | 0 | 5 | 7 | 0 | 20 | 27 | 4 | 42
[10 empty] | 9 | 0 | 9 | 4 | 0 | 4 | 3 | 16 | 0 | 19 | 7 | 35
[10 empty] | 7 | 0 | 7 | 4 | 9 | 13 | 6 | 0 | 0 | 6 | 6 | 19
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 6 | 0 | 0 | 6 | 7 | 22
[10 empty] | 8 | 0 | 8 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 7 | 18
[10 empty] | 10 | 2 | 12 | 5 | 0 | 5 | 3 | 16 | 20 | 39 | 7 | 58
[10 empty] | 11 | 0 | 11 | 4 | 0 | 4 | 3 | 0 | 0 | 3 | 6 | 20
[10 empty] | 8 | 0 | 8 | 5 | 0 | 5 | 5 | 0 | 20 | 25 | 7 | 40
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 5 | 16 | 0 | 21 | 6 | 34
[10 empty] | 7 | 0 | 7 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 17
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 2 | 16 | 20 | 38 | 5 | 52
[10 empty] | 9 | 0 | 9 | 3 | 0 | 3 | 3 | 0 | 0 | 3 | 7 | 19
[10 empty] | 10 | 0 | 10 | 3 | 0 | 3 | 4 | 0 | 20 | 24 | 7 | 41
[10 empty] | 9 | 2 | 11 | 4 | 0 | 4 | 5 | 0 | 0 | 5 | 6 | 22
[10 empty] | 7 | 0 | 7 | 4 | 0 | 4 | 4 | 16 | 20 | 40 | 6 | 53
[10 empty] | 8 | 2 | 10 | 4 | 9 | 13 | 5 | 16 | 20 | 41 | 6 | 57
[10 empty] | 9 | 0 | 9 | 5 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 19
[10 empty] | 9 | 0 | 9 | 2 | 9 | 11 | 7 | 0 | 0 | 7 | 5 | 21
[9 empty] | Average |  |  | 8.657 |  |  | 5.702 |  |  |  | 22.736 | 6.472 | 37.865
[9 empty] | Std |  |  | 1.3599 |  |  | 3.9607 |  |  |  | 13.1789 | 1.1209 | 13.2166

## Probability and Impact
Probability | Value | Very Low | Low | Medium | High | Very High
Very High | >75% | 5 | 10 | 15 | 20 | 25
High | >50% | 4 | 8 | 12 | 16 | 20
Medium | >25% | 3 | 6 | 9 | 12 | 15
Low | >10% | 2 | 4 | 6 | 8 | 10
Very Low | <=10% | 1 | 2 | 3 | 4 | 5
| Impact | Very Low | Low | Medium | High | Very High
| Schedule | <1 | <5 | <10 | <15 | <20
| Cost | <$1,000 | <$2,500 | <$5,000 | <$7,500 | <$15,000

## Risk Register
Risk ID | Risk Description | Probability | Schedule Impact | Cost Impact | Schedule Score | Cost Score
R1 | Risk of scope creep | Low | Low | Medium | 2 | 6
R2 | Risk of material availability and timing | High | High | Medium | 16 | 12
R3 | Risk that expert is not available | High | Very High | Medium | 20 | 12
R4 | Risk of weather delays | Medium | Medium | Low | 9 | 6
| Probability | Value | Very Low | Low | Medium | High | Very High
| Very High | >75% | 5 | 10 | 15 | 20 | 25
| High | >50% | 4 | 8 | 12 | 16 | 20
| Medium | >25% | 3 | 6 | 9 | 12 | 15
| Low | >10% | 2 | 4 | 6 | 8 | 10
| Very Low | <=10% | 1 | 2 | 3 | 4 | 5